Project Executive Summary

Investigating the dynamics of return migration in the Republic of Moldova: a qualitative analysis (ReMiReM)

Project code PN-IV-P8-8.3-ROMD-2023-0173

https://fspac.ubbcluj.ro/castle/en/research/research-projects/remirem

The proposed deliverables (1 article submitted for publication; 1 edited volume submitted for publication; 1 policy report published; 1 webinar with Moldovan authorities; 1 international conference) for this phase were fully delivered in accordance with the planned activities. All scientific papers were based on prior literature and policy research, as well as on primary and secondary analysis of field data, comprising both conceptual and empirical results.

The article (co-authored by team member Anatolie Coșciug) has been submitted and accepted for publication in a prestigious international journal.

The volume (edited by the two lead partners) contains papers from all team members from both partners, and is currently being published by a prestigious national publisher.

The policy report drawn up in collaboration between the teams has been published on the project website.

The activities, also 100% completed in Phase 3 of the project (Secondary data analysis and project completion), carried out between 1 January 2026 and 19 May 2026, were implemented as follows.

The secondary data analysis (Act 3.1), coordinated by the lead partner who trained the Moldovan team (Act 3.1.1), was carried out using qualitative sociological research methods by the latter (Act 3.1.2).

The data analysis formed the basis for the production of scientific texts with the participation of the team from Moldova (Act 3.2) through their training and the coordination of the writing process by the lead partner (Act 3.2.1) and, respectively, through their participation in the production of the scientific texts (Act 3.2.2).

The organisation of scientific events (Act 3.3) was also coordinated by the lead partner (Act 3.3.1) with the participation of the partner from Moldova (Act 3.3.2) and resulted in the delivery of the two events envisaged in the project, as follows. A hybrid roundtable was organised at ASEM, Chișinău, with the participation of members of both partners, as well as numerous representatives of relevant institutions in Moldova (“authorities webinar”, deliverable), at which the policy report developed during this phase was also launched. An international workshop was also organised in Cluj-Napoca, a scientific event with prominent participants, including team members (“international conference”, deliverable), where the content of the edited collective volume was launched (the volume itself is currently being published).